## Capacity Allocation
Team | Composition |  |  |  | Available Week |  |  |  | Capacity Used |  |  |  | Remaining Capacity |  |  |  | % of Remaining Capacity
| BE | FE | FS | QA | BE | FE | FS | QA | BE | FE | FS | QA | BE | FE | FS | QA
Team 1 | Composition BE: 1; Composition FE: 1; Available Week BE: 13; Available Week FE: 5; Remaining Capacity BE: 13; Remaining Capacity FE: 5; Remaining Capacity FS: 0; Remaining Capacity QA: 0 | 1800%
Team 2 | Capacity Used BE: 5; Capacity Used FE: 0; Capacity Used QA: 0; Remaining Capacity BE: -5; Remaining Capacity FE: 0; Remaining Capacity FS: 0; Remaining Capacity QA: 0 | #DIV/0!
Team 3 | Capacity Used BE: 0; Capacity Used FE: 0; Capacity Used QA: 0; Remaining Capacity BE: 0; Remaining Capacity FE: 0; Remaining Capacity FS: 0; Remaining Capacity QA: 0 | #DIV/0!
Team 4 | Capacity Used BE: 0; Capacity Used FE: 0; Capacity Used QA: 0; Remaining Capacity BE: 0; Remaining Capacity FE: 0; Remaining Capacity FS: 0; Remaining Capacity QA: 0 | #DIV/0!
Team 5 | Capacity Used BE: 0; Capacity Used FE: 0; Remaining Capacity BE: 0; Remaining Capacity FE: 0; Remaining Capacity FS: 0; Remaining Capacity QA: 0 | #DIV/0!
Team 6 | Capacity Used BE: 0; Capacity Used FE: 0; Remaining Capacity BE: 0; Remaining Capacity FE: 0; Remaining Capacity FS: 0; Remaining Capacity QA: 0 | #DIV/0!
Team 7 | Capacity Used BE: 0; Capacity Used FE: 0; Remaining Capacity BE: 0; Remaining Capacity FE: 0; Remaining Capacity FS: 0; Remaining Capacity QA: 0 | #DIV/0!
| 1 | 1 | 0 | 0 | 13 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 8 | 5 | 0 | 0
[6 empty] | Total Capacity used (%) |  |  | 38.46% | 0% | #DIV/0! | #DIV/0! | 61.54% | 100% | #DIV/0! | #DIV/0!

## Summary
[Group/Module Name] (PIC1, PIC2) |  | Team | Status | ETA | [Group/Module Name] (PIC1, PIC2) |  | Team | Status | ETA | [Group/Module Name] (PIC1, PIC2) |  | Team | Status | ETA
1 | Module/Feature 1 | VAL | To Do | 2024-07-09 | 1 | Module/Feature 1 | WHS | To Do | 2024-07-10 | 1 | Module/Feature 1 | IPM
2 | Module/Feature 2 | VAL | To Do | 2024-08-20 | 2 | Module/Feature 2 | WHS | To Do | 2024-07-25 | 2 | Module/Feature 2 | IPM |  | 2024-07-30
3 | Module/Feature 3 | VAL | To Do | 2024-08-16 | 3 | Module/Feature 3 | WHS | To Do | 2024-07-31 | 3 | Module/Feature 3 | IPM |  | 2024-08-30
[Group/Module Name] (PIC1, PIC2) |  | Team | Status | ETA | [Group/Module Name] (PIC1, PIC2) |  | Team | Status | ETA | [Group/Module Name] (PIC1, PIC2) |  | Team | Status | ETA
1 | Module/Feature 1 | INVA | To Do | 2024-07-09 | 1 | Module/Feature 1 | INVA | To Do | 2024-07-09 | 1 | Module/Feature 1 | PRO | To Do | 2024-07-09
2 | Module/Feature 2 | INVA | To Do | 2024-08-20 | 2 | Module/Feature 2 | INVA | To Do | 2024-08-20 | 2 | Module/Feature 2 | PRO | To Do | 2024-08-20
3 | Module/Feature 3 | INVA | To Do | 2024-08-16 | 3 | Module/Feature 3 | INVA | To Do | 2024-08-16 | 3 | Module/Feature 3 | PRO | To Do | 2024-08-16

## Roadmap
Team Name
YYQN
July |  |  |  |  | August |  |  |  | September
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Module 2 : 30 Aug 2024
Module 1 : 20 Aug
Module 3 : 30 Sept 2024
Module 4 : 30 Sept 2024
Module 5 : 8 Aug
Module 6 : 22 Aug
Module 7 : 27 Aug
Module 8: XX
Module 9: XX
Module 10: XX

## RFC
| RFC Title | Team | Status | ETA | Require further decision? | Open Items | Link
1 | RFC 1 | VAL | Ready to Review |  | TRUE | - Discuss related toggling | RFC Link 1
2 | RFC 2 | INVA | Need Revision | Review 1: 9 July 2024 Review 2: (ETA) 23 July 2024 | FALSE | 18/07 -- ETA solved 23/07 - Redis - API contract - POC DB result | RFC Link 2
3 | RFC 3 | WHS | In Progress |  | FALSE |  | RFC Link 3

## Collaboration Timeline
|  | Activity / Task Outline | Status | Team | PIC | Dur | Notes/Reference | 2024-07-01 | [24 empty] | 2024-08-01 | [19 empty] | 2024-09-01 | [20 empty] | 2024-10-01 | [23 empty] | 2024-11-01
[8 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 | [6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
[8 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
General Step
| RFC Creation & API Contract |  | Done | All | bar: Week 1 1 to Week 2 9
| UIUX Designing |  | In Progress | All | bar: Week 1 1 to Week 2 9
[Team Name] (Team Composition) -- Timeline Status
Milestone 1
|  | Task Outline 1 |  |  |  | 2 | need confirm from product team 18/07 - Need further discussion about the API integration consumed by user - Regardless the package, toggle will be on the CID level 23/07 - there is changes at onboarding flow: here | bar: Week 1 5 to Week 2 16
Task Outline 2 | bar: Week 1 5 to Week 2 16
Milestone 2
|  | Task Outline 1 |  |  |  | 2 | bar: Week 3 19 to Week 4 30
Team 1 (3 BE, 2 FE) -- DRAFT, need more discussion
Milestone 1
|  | Task Outline 1 |  |  |  | 2 | bar: Week 1 5 to Week 2 16
Task Outline 2 | bar: Week 1 5 to Week 2 16
Milestone 2
|  | Task Outline 1 |  |  |  | 2 | bar: Week 3 19 to Week 4 30
Task Outline 2 | bar: Week 3 19 to Week 4 30

## To Do
ETA | To Do List | Active Team Marker | Relevant Personel | Status | Notes (highlight/update of the topic, MoM meeting)
| List down the initiative and link to task breakdown | TPM | Winda | Won't Fix
2024-08-15 | To Do 1 | Others |  | In Discussion | Current Some report already in candidate as not real time report Next Discusion with data team - Winda
| To Do 2 | INVB |  | Done
| To Do 3 | DevOps/DBOps |  | Blocker

## Task OutlineBreakdown
Task Outline / Breakdown | Details |  | Team | Expertise | Effort (in man week)
| Subtask | Dependencies
Predevelopment |  |  | INVA |  | 0
Setup environment |  |  |  |  | 0
Learning new stack/product domain |  |  |  | BE | 10
RFC, Impact Analysis and Approval Process |  |  |  |  | 0
Milestone 1
Task 1 | - create form - create api for xxx use case - integration - create new table - unit test - development test by developer - PR review |  | IPM | BE | 5
Task |  |  |  | FE | 6
Task |  |  |  |  | 0
Task |  |  |  |  | 0
Task |  |  |  |  | 0
Milestone 2
Task |  |  |  |  | 6
Task |  |  |  |  | 0
Task |  |  |  |  | 0
Milestone 3
Task |  |  |  |  | 0
Task |  |  |  |  | 0
Task |  |  |  |  | 0
Task |  |  |  |  | 0
Task |  |  |  |  | 0
|  |  |  | Capacity Summary : | 21
|  |  |  | BE Total Effort : | 15
|  |  |  | FE Total Effort : | 6
|  |  |  | QA Total Effort : | 0
|  |  |  | iOS Total Effort : | 0
|  |  |  | Android Total Effort : | 0

## Risk & Mitigation
No | Squad | Planned/Unplanned | Risk Type | Risk Description | Risk Probability | Risk Impact | (Calculated, don't fill) Risk to Project * | Impacted Initiative (multiple) | Impact Type | Impact Detail | Mitigation State | Mitigation Plan Detail | Mitigation Status
| IPM | Planned | Scope Risk, Dependency Risk, People Risk |  | Medium | High | High |  | Operational |  | Minimise the risk
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
* Notes:
1. If Risk to Project is "High", team to arrange sync with head levels to design the mitigation plan 2. All risk type must be acknowledged by head levels

## RACI
R | Responsible | 1. The person who actually carries out the process or task assignment 2. Responsible to get job done
A | Accountable | 1. The person who is ultimately for process or task being completely appropriately 2. Responsible person(s) are accountable to this person
C | Consulted | 1. People who are not directly involved with carrying out task, but who are consulted 2. Maybe stakeholder, or subject matter expert
I | Informed | 1. Those who receive output from the process or task, or who have a need to say informed
No | Module/Feature/Function | R | A | C | I | Remarks

## Limitation
No | Initiative Name | Use Case | Squad | Limitation Description | Solution